## Dashboard
CipherHealth Marketing Plan Tracker — Q3-Q4 2026
Last updated | 2026-08-06
Marketing lead | [Assign owner]
Plan status | Draft — pending 6 leadership decisions
Metric | Target | Actual / Plan | Attainment | Notes
Q3 Marketing Pipeline | $2.2M | $240K | 11% | Critical gap — Sept/Oct recovery plan targets ~$1.4M new pipe
Q4 Marketing Pipeline | $1.6M | TBD | — | Depends on NGPX + CCI moment
Q3-Q4 Ad Budget (planned) | $124K ($31K/mo) | $124K | 100% allocated | Leadership decision: approve $40-45K/mo or accept lower recovery
Sept/Oct New Pipe Target | ~$1.4M | — | — | Even at 100% hit, Q3 closes ~73% ($1.6M of $2.2M)
Strategic Pillars (tag every row)
1. Pipeline Recovery — close Q3 gap, set up Q4/November pipeline
2. Product Narrative — hero webinar + CCI reveal positioning
3. Customer Proof — panel webinars, case studies, reference selling
4. Field & Community — CX Exchange, NGPX, Beryl regional chapters

## September 2026
Week Of | Category | Pillar | Activity / Deliverable | Owner | Status | Pipeline $ Target | Notes / Dependencies
2026-09-01 | Lead Gen | Pipeline Recovery | Paid search + LinkedIn campaign launch (pending budget approval) | Jen | Not Started | $60K | Creative blocked on positioning decision
2026-09-01 | Content | Product Narrative | Webinar landing page + save-the-date email #1 | Christy | Not Started | $50K | Needs customer name by Aug 15
2026-09-01 | PR | Product Narrative | Optional: trade press outreach for Sept 24 webinar | Christy | Not Started | $25K | Only if positioning locked early
2026-09-08 | Lead Gen | Pipeline Recovery | Webinar promo email #2 + paid retargeting | Jen | Not Started | $80K
2026-09-08 | Content | Customer Proof | Customer proof asset — stat card + quote approval | Christy | Not Started | $25K | UM Health / Penn / Norton
2026-09-08 | Field | Field & Community | Beryl regional chapter #1 — logistics + invite list | Joy | Planning | $75K | Chapter TBD by Joy
2026-09-15 | Lead Gen | Pipeline Recovery | Webinar promo email #3 + 1:1 AE outreach to target accounts | Jen + AEs | Not Started | $120K | AE team: top 50 accounts
2026-09-15 | Content | Product Narrative | Speaker prep + dry run (Zach + customer + PM) | Jen + PM | Not Started |  | Contractor runs production
2026-09-15 | Retention | Customer Proof | CS reference outreach for Oct 22 panel | CS | Not Started
2026-09-22 | Lead Gen | Pipeline Recovery | Final reg push + day-of reminders | Jen | Not Started | $100K
2026-09-24 | Lead Gen | Product Narrative | HERO WEBINAR — Zach + Product + Customer | Jen + PM | Planning | $500K | Primary September pipe event
2026-09-22 | Content | Customer Proof | Post-webinar nurture sequence + recording gated asset | Christy | Not Started | $50K | Launch Sept 25

## October 2026
Week Of | Category | Pillar | Activity / Deliverable | Owner | Status | Pipeline $ Target | Notes / Dependencies
2026-10-06 | Lead Gen | Pipeline Recovery | October paid campaign — customer proof angle | Jen | Not Started | $60K
2026-10-06 | Content | Customer Proof | Oct 22 panel landing page + speaker bios | Christy | Not Started | $40K
2026-10-06 | Field | Field & Community | CX Exchange East prep — meetings, booth, materials | Joy | Blocked | $200K | CONFIRM attendance by Aug 15
2026-10-12 | Conference | Field & Community | CX Exchange East (Oct 12-13) | Joy + AEs | Under consideration | $200K | 2-day event
2026-10-13 | Field | Field & Community | Beryl regional chapter #2 | Joy | Planning | $75K | Chapter TBD
2026-10-20 | Lead Gen | Customer Proof | Oct 22 panel promo blitz | Jen | Not Started | $80K
2026-10-22 | Lead Gen | Customer Proof | CUSTOMER PANEL WEBINAR | Jen | Planning | $400K | 2-3 customer speakers
2026-10-27 | Content | Pipeline Recovery | Q4 pipeline content — CCI teaser | Christy + PM | Not Started | $50K | Feed Nov 12 reveal
2026-10-27 | Retention | Customer Proof | Post-panel nurture + case study draft | Christy | Not Started | $30K

## Social Calendar
Week Of | Day | Owner | Pillar | Channel | Topic / Hook | Asset Needed | Status | Publish Date
2026-09-01 | Mon | Zach | Product Narrative | LinkedIn | AI infrastructure positioning teaser (pending Aug 15 lock) | Static + quote card | Not Started | 2026-09-02
2026-09-01 | Tue | Jen | Pipeline Recovery | LinkedIn | Sept 24 webinar save-the-date | Webinar graphic | Not Started | 2026-09-03
2026-09-01 | Wed | Joy | Field & Community | LinkedIn | Beryl regional chapter preview | Event photo / logo | Not Started | 2026-09-04
2026-09-01 | Thu | Christy | Customer Proof | LinkedIn | Customer outcome stat (UM Health or selected customer) | Stat card | Not Started | 2026-09-05
2026-09-01 | Fri | Exec (rotate) | Pipeline Recovery | LinkedIn | Thought leadership — care coordination at scale | Exec headshot | Not Started | 2026-09-06
2026-09-08 | Mon | Zach | Product Narrative | LinkedIn + X | Product + customer co-presenter announcement | Speaker bios | Not Started | 2026-09-09
2026-09-08 | Tue | Jen | Pipeline Recovery | LinkedIn | Webinar registration push #1 | Registration link | Not Started | 2026-09-10
2026-09-08 | Wed | Joy | Field & Community | LinkedIn | CX Exchange East — confirm or pivot message | Event badge | Blocked | 2026-09-11
2026-09-08 | Thu | Christy | Customer Proof | LinkedIn | Customer quote / mini case | Approved quote | Not Started | 2026-09-12
2026-09-08 | Fri | Exec (rotate) | Product Narrative | LinkedIn | Why now: operational AI in health systems | Blog link | Not Started | 2026-09-13
2026-09-15 | Mon | Zach | Product Narrative | LinkedIn | Webinar agenda reveal — 3 takeaways | Agenda graphic | Not Started | 2026-09-16
2026-09-15 | Tue | Jen | Pipeline Recovery | LinkedIn + Email | Webinar registration push #2 (48hr urgency) | Countdown creative | Not Started | 2026-09-17
2026-09-15 | Wed | Joy | Field & Community | LinkedIn | Beryl chapter meeting recap or promo | Chapter logo | Not Started | 2026-09-18
2026-09-15 | Thu | Christy | Customer Proof | LinkedIn | Speaker spotlight — customer executive | Headshot | Not Started | 2026-09-19
2026-09-15 | Fri | Exec (rotate) | Pipeline Recovery | LinkedIn | Pipeline / market POV | — | Not Started | 2026-09-20
2026-09-22 | Mon | Zach | Product Narrative | LinkedIn | 24-hour webinar countdown | Live badge | Not Started | 2026-09-23
2026-09-22 | Tue | Jen | Pipeline Recovery | LinkedIn + Email | Final registration push | Reminder email | Not Started | 2026-09-23
2026-09-22 | Wed | Joy | Field & Community | LinkedIn | Live-tweet/webinar day-of thread | Hashtag set | Not Started | 2026-09-24
2026-09-22 | Thu | Christy | Customer Proof | LinkedIn | Post-webinar thank you + recording CTA | Recording link | Not Started | 2026-09-25
2026-09-22 | Fri | Exec (rotate) | Customer Proof | LinkedIn | Key takeaway from Sept 24 session | Clip / quote | Not Started | 2026-09-26

## Webinars
Date | Title (working) | Type | Speakers | Customer | PM Owner | Mktg Owner | Reg Target | Pipe Target | Producer | Status | Promo Start | Notes
2026-09-24 | Hero Product Webinar — Care Coordination / AI Infrastructure (TBD positioning) | Hero launch | Zach + Product + Customer executive | TBD — UM Health / Penn / Norton (Henry Ford backup) | [Product Marketing] | Jen | 300 | $500K | Contractor $8-12K (pending approval) | Planning | 2026-09-03 | Lock customer by Aug 15; positioning language by Aug 15
2026-10-22 | Customer Panel — Operational Outcomes at Scale | Customer proof | 2-3 customers + moderator | Panel TBD | [Product Marketing] | Jen | 250 | $400K | Same contractor | Planning | 2026-10-01 | Recruit panelists from Sept 24 registrants + CS references
2026-11-12 | CCI Reveal — Product Moment | Feature launch | Product + Zach | N/A | [Product Marketing] | Jen | 350 | $500K | Internal or contractor | Not Started | 2026-10-20 | Anchor Q4 pipeline; coordinate with product GA timing

## Field Events
Date | Event | Type | Location | Owner | Budget | Pipe Target | Status | Notes
2026-09 TBD | Beryl Institute Regional Chapter #1 | Regional field | TBD — Joy selects | Joy | $2-4K | $75K | Planning | Layer local field events under ElevatePX national Q1 narrative
2026-10 TBD | Beryl Institute Regional Chapter #2 | Regional field | TBD — Joy selects | Joy | $2-4K | $75K | Planning | Pick chapters with active member hospitals in ICP
2026-10-12 | CX Exchange East | Conference | East (TBD city) | Joy + AE team | $8-15K | $200K | Under consideration | CONFIRM by Aug 15 — recommend yes if 3+ target accounts attending
2026-12-02 | NGPX | Conference / Sponsorship | Palm Springs | Jen + Events | Confirmed sponsorship | $450K | Confirmed | Anchor Q4 pipeline; book meetings by Nov 1

## Pipeline Targets
Month | Source | Target ($) | Actual ($) | Attainment % | Owner | Notes
2026-09 | Paid digital | $180K |  |  | Jen | Requires $40-45K/mo budget approval vs $31K plan
2026-09 | Webinar (Sept 24) | $500K |  |  | Jen | Hero webinar — primary September pipe driver
2026-09 | Field / Beryl regional | $75K |  |  | Joy | Chapter meeting #1
2026-09 | Content / inbound | $100K |  |  | Christy | Gated assets + nurture
2026-09 | TOTAL | $855K | $240K YTD Q3 | 11% Q3 YTD | Marketing | Sept alone won't close full Q3 gap
2026-10 | Paid digital | $180K |  |  | Jen
2026-10 | CX Exchange East | $200K |  |  | Joy | Contingent on Aug 15 confirmation
2026-10 | Webinar (Oct 22 panel) | $400K |  |  | Jen
2026-10 | Field / Beryl regional | $75K |  |  | Joy | Chapter meeting #2
2026-10 | Content / inbound | $100K |  |  | Christy
2026-10 | TOTAL | $955K |  |  | Marketing | Combined Sept+Oct ~$1.4M new pipe target
2026-11 | Paid digital | $180K |  |  | Jen
2026-11 | Webinar (Nov 12 CCI) | $500K |  |  | Jen + PM | Product moment
2026-11 | Field / retention | $150K |  |  | CS + Marketing | Customer expansion campaigns
2026-11 | TOTAL | $830K |  |  | Marketing
2026-12 | NGPX | $450K |  |  | Jen | Confirmed sponsorship
2026-12 | Paid digital | $180K |  |  | Jen
2026-12 | Retention / year-end | $200K |  |  | Christy
2026-12 | TOTAL | $830K |  |  | Marketing | Q4 attainment decided here

## Open Decisions
# | Decision | Options | Owner | Due Date | Status | Impact if delayed
1 | Lock positioning language | AI infrastructure vs care coordination infrastructure | Executive + PM | 2026-08-15 | Open | Blocks all Sept 24 creative, ads, and webinar title
2 | Confirm CX Exchange East attendance | Attend vs skip | Joy + Jen | 2026-08-15 | Open | $200K Oct pipe at risk
3 | Approve ad budget increase | $40-45K/mo vs $31K plan | Chris (CFO) | 2026-08-15 | Open | Lower paid pipe recovery in Q3-Q4
4 | Approve webinar producer contractor | $8-12K for Sept 24 + Oct 22 | Jen Thomas | 2026-08-15 | Open | Production quality / on-time delivery risk
5 | Select Sept 24 customer speaker | UM Health / Penn / Norton (Henry Ford backup) | CS + Zach | 2026-08-15 | Open | Cannot finalize promo without named customer
6 | Select two Beryl regional chapters | Joy to recommend based on ICP density | Joy | 2026-08-22 | Open | Field event logistics and local pipe

## Measurement
Cadence | Metric | Owner | Distribution | Next Due
Weekly | Pipeline created by source vs target | Jen | Marketing standup + SLT slack | Every Monday
Weekly | Webinar reg / attendance / pipe | Jen | Marketing standup | Every Monday
Weekly | Paid media spend vs CPA | Jen | Marketing + Finance | Every Friday
Monthly | Marketing-sourced pipeline attainment | Jen | CSO + CFO | First business day
Monthly | Content / social engagement vs plan | Christy | Marketing team | First business day
Monthly | Event ROI (meetings held, pipe) | Joy | Marketing + Sales | Within 5 days post-event
Quarterly | Q3/Q4 pipeline vs annual plan | Jen | Board / exec team | Quarter close + 10 days

## Q4 Outline
Week Of | Category | Activity | Owner | Status | Pipe Target | Notes
2026-11-03 | Lead Gen | Nov paid campaign launch — CCI teaser | Jen | Not Started | $180K
2026-11-03 | Content | CCI reveal content sprint begins | Christy + PM | Not Started
2026-11-10 | Feature Launch | Nov 12 CCI Reveal webinar | Jen + PM | Planning | $500K | Anchor Q4 product moment
2026-11-17 | Retention | Customer expansion email series | Christy | Not Started | $75K
2026-11-24 | Lead Gen | NGPX pre-book meeting campaign | Jen + Joy | Not Started | $100K | Target accounts only
2026-12-01 | Conference | NGPX Dec 2-4 Palm Springs | Jen + Events | Confirmed | $450K | Confirmed sponsorship
2026-12-08 | Retention | Year-end customer thank-you + renewal touch | Christy + CS | Not Started | $100K
2026-12-15 | Lead Gen | Q1 2027 pipeline seeding — ElevatePX / Beryl | Joy | Not Started | $50K | Bridge to national ElevatePX Q1